## Pending Presidential Pledges
S/N | PLEDGE | SUBSECTOR | DISTRICT/ LOCATION | FACILITIES
1 | Kal Aloi Parents School 3rd November 2015 | Primary | Agago | Build into a modern primary school with teachers' quarters.
2 | Igrah Women Group (Primary school) | Primary | Arua | Construction of four classrooms
3 | Kachumbala Catholic Mission 9 June 2013 | Primary | Bukedea | Construction of a primary school in war affected region of Kachumbala during 1986 war
4 | Bughanga Primary School 21 january 2014 | Primary | Butaleja | Construction of a modern Government aided primary school in Budumba sub-county, West Bunyole.
5 | Kisozi Primary School 19/04/2014 | Primary | Gomba | Development of the school
6 | Lumanyo Primary School 19/04/2014 | Primary | Gomba | Development of the school
7 | Bulera Primary School 19/04/2014 | Primary | Gomba | Development of the school
8 | Palenga P/S 1 june 2009 | Primary | Gulu | 12 cl/rooms NC, Office & store , a kitchen, 300 desks 3 No 5 stance latrine, 2 No 10,000 litre water tanks, (1st & 2nd Installment)
9 | Mary Queen of Peace Mixed Day and Boarding Primary School 27th October 2017 | Primary | Gulu | Construction of a dormitory.
10 | Bulanga Primary School 9th November 2016 | Primary | Iganga | rehabilitation of school structures
11 | St. Florence Nursery and Primary School 8th October 2017 | Primary | Jinja MC | Construction of a Nursery and Primary School at Kikaramoja Village, Masese III, Walukuba Division.
12 | Mashongora Primary School 29 july 2012 | Primary | Kabarole | Construction of a Primary School in Hakibaale Sub county, Burahya County
13 | Otuboi P/S | Primary | Kaberamaido | 7 cl/rooms, 10 stance latrines, Office & store - 10,000 litre water tank
14 | Kalongo Girls Primary School 9th November 2016 | Primary | Kalongo | Construction of one block of teachers' houses
15 | Makerere Yellow Primary School - Kubiri 29th May 2018 | Primary | Kampala | Renovation and Rehabilitation of the school.
16 | Lwanyama Primary School 26 august 2012 | Primary | Kamuli | Construction of a modern Primary School in Kisozi sub county
17 | Buterimire Primary School 25th May 2018 | Primary | Kamuli | Construction of Teachers' Houses and Fencing the school.
18 | Kabatunda Primary School 9th February 2015 | Primary | Kasese | re-building of the school
19 | Kanyaryeru P/S 5 dec 2013 | Primary | Kiruhura | Repair and rehabilitaion of school
20 | Buruunga Primary School 20th February 2017 | Primary | Kiruhura | Reconstruction of the school at Buruunga - Kazo County.
21 | Yabwengi Primary School 27th January 2016 | Primary | Kiryandongo | Renovation of the school (including sanitation facilities)
22 | St. Kizito Boarding Primary School 25th February 2015 | Primary | Kyankwanzi | Reconstruction of the school.
23 | Nakyesanja P/S 19 october 2009 | Primary | Luwero | Rehabilitation of the school
24 | Nakyesanja P/S 7 November 2016 | Primary | Luwero | Rehabilitation of the school (Phase 2). Pay off balance of 26.813m
25 | Kalasa P/S 17 December 2014 | Primary | Luwero | New building and renovation of Kalasa Primary School
26 | Sam Iga Memorial Primary School 12th February 2015 | Primary | Luwero | Construction of a classroom block
27 | Bombo UMEA Primary School | Primary | Luwero | Rehabilitation of the school
28 | Kaguta Museveni Primary School 17th December 2014 | Primary | Mbale | Build a four classroom block
29 | Mbarara Municipal School 10th March 2016 | Primary | Mbarara | Construction of a Modern Technical Workshop: i) establishment of 2 workshops (540,568,800/=), procurement of standard equipment) Areas are a workshop and classes for Food Science and Technology (100,000,000/=), Knitting and embroidery (150,000,000/=), Computer skills and technology (140,000,000/=), Carpentry and Joinery and Business management ( 150,000,000/=)
30 | Buwama P/S | Primary | Mpigi | Construction of a Primary School
31 | Kalangaalo P/S | Primary | Mubende | Construction of a primary school (1st & 2nd Installment)
32 | Girls Boarding School 17th December 2014 | Primary | Namayingo | Build a Girls Boarding School in Sigulu Islands
33 | Ringe Memorial School 27th October 2017 | Primary | Nebbi | Renovating 2 classrooms blocks, constructing more classrooms and provision of a safe water source. Upgrade to a secondary school. Located in Atego Subcounty.
34 | Barlegi Primary School 11th December 2017 | Primary | Otuke | Completion of the school in Okwang subcounty (completion of 8 classroom block incl. library; construction of HT office, school store, teacher houses and latrines)
1 | Alere Secondary School 3rd August 2015 | Secondary | Adjumani | Purchase of a bus
2 | Adilang Secondary School 9th August 2017 | Secondary | Agago | Develop school into a fully fledged boarding secondary school. Construct teachers' houses, school library, perimeter fence and dormitory facilities. Also provide a bus.
3 | Atyiak Memorial Girls Sec Sch 9 June 2013 | Secondary | Amuru | Construction of a Memorial Girls School in Atyiak sub county in memory of the LRA victims
4 | Apac H.S | Secondary | Apac | Renovation
5 | Maruzi S.S | Secondary | Apac | Construction of a Seed Secondary School (1st & 2nd Phase)
6 | Ikwera Girls' School 3rd August 2015 | Secondary | Apac | Purchase of a bus
7 | Secondary School 17th July 2017 | Secondary | Arua | Construct a Seed Secondary School in Madi Okolo County
8 | Kamuhingi Secondary School | Secondary | Bundibugyo | Construction of Hostel (1st & 2nd Installment)
9 | Dokolo Girls S.S | Secondary | Dokolo | Model S.S.S (1st & 2nd Installment)
10 | Dokolo Girls S.S | Secondary | Dokolo | Model S.S.S (1st & 2nd Installment) Phase 2
11 | Iguli Girls SS | Secondary | Dokolo | 5 classrooms completed, 1 Dormitory block, 5 Stance VIP latrines.
12 | Our Lady of Guadalupe SSS 11th March 2015 | Secondary | Gomba | Construction of a laboratory block
13 | Our Lady of Guadalupe SSS 11th March 2015 | Secondary | Gomba | Construction of a laboratory block (Phase 2)
14 | kisozi senior secondary school 23rd may,2016 | Secondary | gomba | Fencing of the school
15 | Sacred Heart Senior Secondary School 14th June 2018 | Secondary | Gulu | Renovation of the school
16 | Walibo Secondary School | Secondary | Iganga | Construction of Secondary School (1st & 2nd Installment)
17 | Kyezibire SSS | Secondary | Isingiro | Rehabilitation of the school
18 | Ngarama S.S.S | Secondary | Isingiro | Rehabilitation of school
19 | St. Mary’s Rushoroza Vocational Secondary School 9th November 2016 | Secondary | Isingiro | build and grant aid school
20 | Government Aided Secondary School 15th October 2014 | Secondary | Jinja | A Government Aided Secondary School for Buyengo Sub-county
21 | Masese Secondary School 9 June 2013 | Secondary | Jinja MC | Construction of a secondary school on Jinja Municipality East Constituency
22 | Bubare S.S 29 sept 2009 | Secondary | Kabale | Construction of a science laboratory, library and state-of-the-art computer laboratory (1st & 2nd Installment)
23 | St. Paul S.S Bukinda-Rukiga | Secondary | Kabale | Multi-Purpose Science room
24 | kyogo senior secondary school 21st march,2016 | Secondary | kabale | rehabilitation of the school.
25 | Kasenda S S 9 June 2013 | Secondary | Kabarole | Construction of a Seed Secondary School in Kasenda Subcounty which has no secondary School
26 | Karangura SS 29 july 2012 | Secondary | Kabarole | Construction of a Secondary School in Karangura Sub county, Burahya County
27 | Noble Mayombo Memorial School 4th September 2014 | Secondary | Kabarole | Construction of a school
28 | Bishop Balya Community School 4th September 2014 | Secondary | Kabarole | Construction of a school
29 | Lwala Girls SS 14 nov 2013 | Secondary | kaberamaido | School bus for the School
30 | Kansanga Seed Secondary School 4th May 2016 | Secondary | Kampala | computers and 12 classrooms block and teachers' houses.
31 | Mbulamuti Secondary School 17th December 2014 | Secondary | Kamuli | Build a science laboratory for a Secondary School in Mbulamuti.
32 | Busoga High School 25th September 2017 | Secondary | Kamuli | Infrastructure development
33 | Bwizi Seed SS 21 june 2011 | Secondary | Kamwenge | Construction of seed Secondary School
34 | Kamwenge (Bihanga) 21 june 2011 | Secondary | Kamwenge | Construction of seed Secondary School
35 | Kamwenge S.S | Secondary | Kamwenge | 2 unit school laboratory, library, 2 classrooms, 2 unit staff houses
36 | Rugarama Secondary School 22nd March 2018 | Secondary | Kamwenge | Grant aid the school.
37 | Nyakasenyi Secondary School 22nd March 2018 | Secondary | Kamwenge | Grant aid the school.
38 | Kanara Secondary School 22nd March 2018 | Secondary | Kamwenge | Grant aid the school.
39 | St. Joseph's Kinaaba Community Secondary School | Secondary | Kanungu | Provide support
40 | Gamatui Girls Secondary School | Secondary | Kapchorwa | Construction of Basic infrastructure ICT Block; 2 Domitory blocks; 2 No. blocksof 5-stance lined latrines; Multipurpose dining Hall; Library block and Sick bay.
41 | Gamatui Girls Secondary School | Secondary | Kapchorwa | Construction of Basic infrastructure ICT Block; 2 Domitory blocks; 2 No. blocksof 5-stance lined latrines; Multipurpose dining Hall; Library block and Sick bay. (Phase 2)
42 | Kirigwajjo SSS (Kambuga Kibaale High School) | Secondary | Kibaale
43 | Secondary School 20th February 2017 | Secondary | Kiruhura | Construction of a modern secondary school at Buruunga - Kazo County.
44 | Buruunga Seed Secondary School 20th February 2017 | Secondary | Kiruhura | Construction of a modern secondary school at Buruunga - Kazo County.
45 | Stella Matutina Secondary School 7th February 2016 | Secondary | Kiryandongo | Construct a library, computer laboratory and purchase computers
46 | Francis Ayume Memorial Secondary School 5th March 2018 | Secondary | Koboko | Takeover the school.
47 | Aculbanya Secondary School | Secondary | Kole | Purchase of a bus
48 | Abim Secondary School 9th November 2016 | Secondary | Kotido | construction of a VIP latrine
49 | Kwosir Girls Secondary School | Secondary | Kween | Construction of a boarding secondary school for Sebei sub region
50 | Kwosir Girls Secondary School | Secondary | Kween | Construction of a boarding secondary school for Sebei sub region (Phase 2)
51 | St. Joseph's S.S 27 nov 2013 | Secondary | Kyankwanzi | Rehabilitation of the school
52 | Christ The King SS Kalisizo 23rd August 2018 | Secondary | Kyotera | Provision of a school bus and ICT laboratory
53 | Ngogwe Baskerville Secondary School 9th August 2018 | Secondary | Lugazi MC | Construction of a science laboratory, library, computers, staff and transport facility
54 | Model School 8th December 2017 | Secondary | Luuka | Construction of a model school in Bukapala village, Itakaibulu Parish
55 | Makulubita Secondary School | Secondary | Luwero | Rehabilitation and construction of new structures
56 | Kijunjula Senior Secondary School | Secondary | luwero | Up-grading
57 | Bombo Senior Secondary School | Secondary | Luwero | Rehabilitation of the school and equipping science laboratory
58 | Kalasa College School COU, Wobulenzi 27th July 2018 | Secondary | Luwero | Construction of Staff houses
59 | St. Henry's Kitovu | Secondary | Masaka | Build a science laboratory
60 | St. Charles Lwanga SS Lwebitakuli 9th November 2016 | Secondary | Masaka | construction of classes, laboratory, library, teachers’ houses and latrine stances
61 | Kako Senior Secondary School 14th March 2018 | Secondary | Masaka | Rehabilitation of the school (replacement of asbestos roofs)
62 | St. Basil SS (Our Lady of Apostles) 6th July 2018 | Secondary | Masaka | Construction of a computer room, a school library and an Administration Block
63 | Kabarega S.S.S | Secondary | Masindi | Rehabilitation of the school (1st & 2nd Installment)
64 | Bumayoka Seed Secondary School | Secondary | Mbale | School bus for the School
65 | Mbarara Secondary School 29th November 2014 | Secondary | Mbarara | Acquisition of a school bus.
66 | Nyakayojo Secondary School 9th November 2016 | Secondary | Mbarara | construction of teachers' houses
67 | St. Kizito Secondary School 29-Aug-2015 | Secondary | Mityana | Construction Laboratory
68 | St kizito secondary school-banda 29 august,2015 | Secondary | Mityana | construction fo a laboratory
69 | Moroto High School 3rd August 2015 | Secondary | Moroto | Purchase of a bus
70 | Bulamu Seed SS received on 28August 2014 | Secondary | Mpigi | Constuction of a Girl's Hostel
71 | Kabbo Secondary School | Secondary | Mubende | Construction of a Secondary School (1st & 2nd Installment)
72 | Kabbo Secondary School | Secondary | Mubende | Construction of a Secondary School (1st & 2nd Installment) (Phase 2)
73 | Magungulu S S | Secondary | Mubende | Construction of a Secondary School IN Bagezza Sub county
74 | Kigando S S | Secondary | Mubende | Construction of a Secondary School in Kigando Sub county
75 | Kamusenene S S | Secondary | Mubende | Construction of a Secondary School in Kitumbi sub county
76 | Manyogaseka S S | Secondary | Mubende | Construction of a Secondary School in Manyogaseka sub county
77 | Makokoto S S | Secondary | Mubende | Construction of a Secondary School in makokoto sub county
78 | Kasenyi SS 5/12/16 | Secondary | Mubende | School bus for the School
79 | Arengesiep Secondary School 17th October 2014 | Secondary | Nakapiripirit | Construct a girls' dormitory and a library; acquire a school lorry; construct teachers' houses
80 | Kinyogoga SSS | Secondary | Nakaseke | Turn school into boarding school under Universal Secondary Education (1st & 2nd Installment)
81 | Ngoma SSS | Secondary | Nakaseke | Turn school into boarding school under Universal Secondary Education (1st & 2nd Installment)
82 | budago Senior Secondary School | Secondary | Nakaseke | Up-grading
83 | Ngora High School 17 November 2016 | Secondary | Ngora | Construction of a computer laboratory
84 | Mukura Memorial Secondary School 3rd August 2015 | Secondary | Ngora | Purchase of a bus
85 | Ngora High School 17 November 2016 3rd March 2017 | Secondary | Ngora | Construction of a computer laboratory and provision of 20 computers.
86 | Rukoni S.S 1 june 2009 | Secondary | Ntungamo | Construction of a multi purpose science room
87 | Kyamate Secondary School 26 April 2017 | Secondary | Ntungamo | Provision of school bus
88 | Ngai Secondary School 30th August 2017 | Secondary | Oyam | Reconstruction of the school
89 | Ndagaro Seed Secondary School 5 november 2013 | Secondary | Rubirizi | Provision of a seed Secondary School in Ndangaro Sub-County
90 | Mwongyera Senior Secondary School 30th July 2014 | Secondary | Rubirizi | Grant aiding
91 | St. Mary's Madera Girls S.S.S | Secondary | Soroti | Construction of a dormitory.
92 | Eluru Memorial Senior Secondary School 20th July 2017 | Secondary | Teso region | Complete construction of Secondary School in Kapelebyong
93 | Asinge Secondary School 22nd December 2014 | Secondary | Tororo | Acquisition of a school bus.
94 | St Mary's College Kisubi | Secondary | Wakiso | Construction of a Memorial Dormitory
95 | Ariwa, Kei, Midigo, Lodonga, Drajini, Romogi, Kerwa and Kululu 15 march 2014 | Secondary | Yumbe | Construction of 5 government aided secondary schools in sub counties without
96 | St. Aloysius College, Nyapea 8 feb 2014 | Secondary | Zombo | Fencing of the school
97 | St. Peters Warr Girls S.S.S 24th August 2018 | Secondary | Zombo | Provision of a school bus; construction of teachers' houses; constuction of school fence; recruitment of teachers.

## All Presidential Pledges
S/N | PLEDGE | SECTOR | DISTRICT/ LOCATION | FACILITIES | TOTAL PROJECT AMOUNT | FY 2008/09 | FY 2009/10 | FY 2010/11 | FY 2011/12 | FY 2012/13 | FY 2013/14 | FY 2014/15 | FY 2015/16 | FY 2016/17 | FY 2017/18 | FY 2018/19 | OUTSTANDING | REMARKS
1 | 18 Special Schools for the deaf and blind persons 28 august 2008 | MoES |  | Provide 18 Special Schools for the deaf and blind persons | 18000000000 | [11 empty] | 18000000000 | A project has been approved in which establishement of SNE schools will be handled in a phased manner
2 | Amucu Primary School | Primary | Amuria | 250 bags of cement | 7000000 | 0 | 7000000 | 0 | 0 | 0 | [6 empty] | 0 | Completed
3 | Army Boarding PS | Primary | Yumbe | Construction of a primary school for children of ex combats of UNRF (1st, 2nd & 3rd Phase) | 594874000 | 0 | 287000000 | 100000000 | 100000000 | 78000000 |  | 29874000 |  |  |  |  | 0 | Completed
4 | Rhoda Acen 9 June 2013 | Primary | Amuria | Construction of a primary school in Amusus Parish | 342567173 | [7 empty] | 150000000 | 192567173 |  |  | 0 | Completed 2 Classroom Block, 2 Classroom Block with Office, 72 desks, 4 teachers tables and 4 chairs & one 5-Stance VIP for boys
5 | Kongunga Primary School 9 June 2013 | Primary | Bukedea | Construction of a primary school in war affected region of Kachumbala during 1986 war | 342567173 | [7 empty] | 150000000 | 192567173 |  |  | 0 | Completed successfully under defects
6 | Kachumbala Catholic Mission 9 June 2013 | Primary | Bukedea | Construction of a primary school in war affected region of Kachumbala during 1986 war | 491982560 | [11 empty] | 491982560
7 | Bakulumpagi Memorial P/S | Primary | Mpigi | Construction of a Primary School | 131000000 | 0 | 131000000 | [9 empty] | 0 | Completed
8 | Bitsya PS | Primary | Bushenyi | Construction of 2 classroom block, 4 semi detached staff quarter, 2 latrine block of 5 stances each and 12 latrine block for staff. | 171782040 | 165400000 |  | 6382040 |  | 0 | [6 empty] | 0 | Completed
9 | Kisozi Primary School 19/04/2014 | Primary | Gomba | Development of the school | 999257158 | [11 empty] | 999257158 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
10 | Lumanyo Primary School 19/04/2014 | Primary | Gomba | Development of the school | 999257158 | [11 empty] | 999257158 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
11 | Bulera Primary School 19/04/2014 | Primary | Gomba | Development of the school | 999257158 | [11 empty] | 999257158 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
12 | Buguwa Primary School (Bulawori sub-county) 26 august 2012 | Primary | Kamuli | construction of 4 new cl/rooms block; Office and store; 72 desks, 2 blocks of 5 stance lined latrines each (for boys and girls), 1 Block of 2 units teachers' House; 1 block of 3 stances teachers toilet | 280000000 | [5 empty] | 280000000 | [5 empty] | 0
13 | Bulera Primary School 1 june 2009 | Primary | Hoima | Construction of a fully fledged modern day B/school | 319000000 | 0 | 319000000 | [9 empty] | 0 | Funds Provided
14 | Bunaka P/S | Primary | Luwero | Construction and refurbishment | 150000000 | 0 |  | 150000000 | 0 | 0 | [6 empty] | 0 | Completed
15 | St. Mark Girls P/S | Primary | Luwero | Renovation of the school destroyed by hailstorm | 150000000 | [7 empty] | 150000000 |  |  |  | 0
16 | Buniga Primary School | Primary | Kabarole | Iron sheets and cement | 10000000 | 0 | 10000000 | [9 empty] | 0 | Completed
17 | Busaiga Primary School 29 july 2012 | Primary | Kabarole | Construction of a Primary School in Kichwamba Sub county, Burahya County | 342567173 | [6 empty] | 169136411 | 173430762 |  |  |  | 0 | Completed and commissioned 3 Classroom Block, Completion of 4 Unit Staff House, Renovationof 4 Classroom Block.
18 | Butare Primary School | Primary | Buhweju | Construction of a dormitory and Classrooms | 256500000 | 0 | 0 | 0 | 0 | 0 | 256500000 | [5 empty] | 0 | Completed
19 | Buwama P/S | Primary | Mpigi | Construction of a Primary School | 131000000 | 0 | 131000000 | [9 empty] | 0 | Buildings not yet completed.
20 | Buyiga Island P. S 12 sept 2009 | Primary | Mpigi | Construction of Classroom Blocks (1st & 2nd Installment) | 131000000 | 0 |  | 65500000 | 65500000 | 0 | [6 empty] | 0 | Funds Provided
21 | Cissy Makanga Primary School | Primary | Kampala | Renovation of the primary school (1st & 2nd Installment) | 150000000 | 0 |  | 50000000 | 100000000 | 0 | [6 empty] | 0 | Funds Provided
22 | Dokolo Primary School | Primary | Dokolo | Construction of a model primary school | 131000000 | 0 | 131000000 | [9 empty] | 0 | Funds Provided
23 | Erute Primary School | Primary | Lira | 300 pieces of iron sheets | 7500000 | 0 | 7500000 | [9 empty] | 0 | Completed
24 | Iguli P/S | Primary | Dokolo | 3 cl/rooms block CC, 7 cl/rooms block NC; 10 stance latrine, Office & store, 2 No 10,000 litre water tanks, 180 desks | 120118200 | 0 |  | 120118200 | 0 | 0 | [6 empty] | 0
25 | Kabwangasi P.T.C | Primary | Pallisa | Provision of mode of transport for the PTC. (To purchase Mini bus 30 seater Us$ 71,000) | 195960000 | [5 empty] | 195960000 | [5 empty] | 0 | Completed
26 | Kadindimo Rashid Primary School 14 may 2010 | Primary | Kabarole | Government take over of the school | 240000000 | 0 | [8 empty] | 240000000 |  | 0 | District received funds which were used to compensate the founders of the school for the school land.
27 | Kako Junior School 9 sept 2009 | Primary | Masaka | Renovation and provision of scholastic materials (1st & 2nd Installment) | 250000000 | 0 |  | 50000000 | 100000000 | 0 | [6 empty] | 100000000 | Completed
28 | Kalangaalo P/S | Primary | Mubende | Construction of a primary school (1st & 2nd Installment) | 131000000 | 0 |  | 80000000 | 51000000 | 0 | [6 empty] | 0 | Work is at finishes stage.
29 | Kalangala Local Government Education Office | Primary | Kalangala | Procurement of a Motor Boat for Education Office to facilitate monitoring and inspection of schools (compensation of the one by TDMS damaged in accident) | 108000000 | [5 empty] | 108000000 | [5 empty] | 0 | Funds Provided
30 | Kalasa P/S 1 june 2009 | Primary | Luwero | Construction of Primary school | 131000000 | 0 | 131000000 | [9 empty] | 0 | Completed
31 | Kamuri Primary School | Primary | Isingiro | Construction of 2 classroom blocks Teacher's Chair and Tables. | 62000000 | 0 | 62000000 | [9 empty] | 0 | Completed
32 | Kamwenge Catholic Primary School 4 march 2014 | Primary | Kamwenge | Construction of Primary School funded by Kamwenge Catholic Church but grant aided. | 342567173 | 0 | [6 empty] | 150000000 | 192567173 |  |  | 0 | Completed successfully
33 | Kangave P/S 1 june 2009 | Primary | Luwero | Construction of Primary school | 131000000 | 0 | 131000000 | [9 empty] | 0 | completed
34 | Kanyaryeru P/S 5 dec 2013 | Primary | Kiruhura | Repair and rehabilitaion of school | 200000000 | [9 empty] | 200000000 |  | 0 | School received funds. Construction of 2No. 4 unit staff houses and 2No. 2 stance latrines at excavation stage (pit excavation for latrines and strip excavation for staff houses are complete).
35 | Kapeeka P/S | Primary | Nakaseke | Construction of 4 classrooms | 90400000 | 0 |  | 90400000 | 0 | 0 | [6 empty] | 0 | completed
36 | Karugaya P/S | Primary | Kabarole | Iron sheets and cement | 10000000 | 0 |  | 10000000 | 0 | 0 | [6 empty] | 0 | completed
37 | Katugunda P/S | Primary | Kabarole | Iron sheets and cement | 10000000 | 0 |  | 10000000 | 0 | 0 | [6 empty] | 0 | Funds were provided. Iron sheets were bought and re-roofing was done for the classrooms
38 | Kinoni Primary School | Primary | Kabarole | Construct 6 classrooms for the school - 2No. 3-classroom blocks, classroom furniture, lightning system and water harvesting system | 110060000 | 0 |  |  | 110060000 |  |  | 0 |  |  |  |  | 0
39 | Kinyampanika P/S | Primary | Kabarole | Iron sheets and cement | 10000000 | 0 |  | 10000000 | 0 | 0 | [6 empty] | 0 | completed
40 | Kirolo Umea P/S | Primary | Wakiso | Constructed 2 classroom blocks of 2 classrooms each and 4 unit staff house with a toilet | 151400000 | 151400000 | [10 empty] | 0 | The District is yet to give progress
41 | Kisomoro Primary School | Primary | Kabarole | Construct 6 classrooms for the school - 2No. 3-classroom blocks, classroom furniture, lightning system and water harvesting system | 110060000 | 0 |  |  | 110060000 | [7 empty] | 0 | Completed
42 | Kitete P/S -Sekanyonyi S/C | Primary | Mityana | Construction of a primary school | 131000000 | 0 | 0 | 80000000 | 51000000 | 0 | [6 empty] | 0 | completed
43 | KK Kindergarten Nursery & PS | Primary | Rukungiri | Construction of an Office & Classroom block | 50000000 | 0 |  | 50000000 | 0 | 0 | [6 empty] | 0 | completed
44 | Kyamusisi P/S 1 june 2009 | Primary | Mityana | Construction of a primary school | 131000000 | 0 | 131000000 | [9 empty] | 0 | completed
45 | Kyebe CoU Primary School | Primary | Rakai | Construction of a primary school (1st & 2nd Installment) | 131000000 | 0 |  | 80000000 | 51000000 | 0 | [6 empty] | 0 | completed
46 | Lwanyama Primary School 26 august 2012 | Primary | Kamuli | Construction of a modern Primary School in Kisozi sub county | 595101468 | [6 empty] | 200000000 |  |  |  | 200000000 | 395101468
47 | Madera School | Primary | Soroti | Completion of a Primary School | 50000000 | 0 | 50000000 | [9 empty] | 0 | Completed
48 | Mashongora Primary School 29 july 2012 | Primary | Kabarole | Construction of a Primary School in Hakibaale Sub county, Burahya County | 595101468 | [6 empty] | 0 | 200000000 | 279078799 |  | 116022669 | 0 | Completed and commissioned 2 No. 2 Classroom Blocks, 3 Classroom Block with Office, 5 Stance VIP, 2 Unit Staff House with 2 Stance VIP
49 | Moses Kipsiro | PES |  | 50 millions for purchase of a car | 50000000 |  |  |  |  | 50000000 | [6 empty] | 0 | Funds were released
49 | Nakyesanja P/S 19 october 2009 | Primary | Luwero | Rehabilitation of the school | 140000000 | 0 |  | 70000000 | 0 | 70000000 | [6 empty] | 0
50 | Nakyesanja P/S 7 November 2016 | Primary | Luwero | Rehabilitation of the school (Phase 2). Pay off balance of 26.813m | 26813000 | [10 empty] | 26813000 | 0
51 | Nalugi P/S 1 june 2009 | Primary | Mityana | Construction of a primary school | 131000000 | 0 | 131000000 | [9 empty] | 0 | completed
52 | Nampewo P/S | Primary | Mityana | Construction of a primary school | 131000000 | 0 | 131000000 | [9 empty] | 0 | completed
53 | Namutumba Demonstration P/S | Primary | Mityana | Construction of a primary school | 131000000 | 0 | 131000000 | [9 empty] | 0 | completed
54 | Ndeeba Primary School 16 April 2014 | Primary | Kayunga | Rehabilitation works | 100000000 | [6 empty] | 100000000 |  |  |  |  | 0
55 | Nkokonjeru PTC | Dev't Proj | MoES | Classrooms and Domitories | 800000000 |  | 800000000 | [9 empty] | 0 | Paid from devt of PTCs
56 | Nkoyoyo Boarding P/S | Primary | Buikwe | Renovation and provision of scholastic materials | 100000000 | 0 |  | 100000000 | 0 | 0 | [6 empty] | 0 | completed
57 | Nyamigoyi Primary School 25 july 2012 | Primary | Kanungu | Construction of a 3 classroom block | 70787742 | [5 empty] | 70787742 | [5 empty] | 0 | Completed
58 | Otuboi P/S | Primary | Kaberamaido | 7 cl/rooms, 10 stance latrines, Office & store - 10,000 litre water tank | 190363035 | 0 |  |  | 0 | 0 |  | 0 |  | 88199582 |  | 102163453 | 0 | Completed Construction of 5 classrooms (3 classroom block and 2-classroom block with office, 2-Stance VIP, 5-Stance VIP and provision of furniture
59 | Lwala Boys P/S 8 feb 2014 | Primary | Kaberamaido | Construct a new classroom block (3 classroom block) | 70787742 | [7 empty] | 70787742 |  |  |  | 0 | Completed and commissioned Two Blocks of Two classrooms each
60 | Palenga P/S 1 june 2009 | Primary | Gulu | 12 cl/rooms NC, Office & store , a kitchen, 300 desks 3 No 5 stance latrine, 2 No 10,000 litre water tanks, (1st & 2nd Installment) | 191016680 | 0 |  | 70000000 | 121016680 | 0 | [6 empty] | 0 | Funds Provided -Works partly completed
61 | Semuto P/S 1 june 2009 | Primary | Nakaseke | Construction of a primary school | 131000000 | 0 | 131000000 | [9 empty] | 0 | Completed
62 | Shepherd Twin Age Infant School Wankuluku | Primary | Kampala | Cement and other building materials plus furniture | 25000000 | 0 | 25000000 | [9 empty] | 0 | Funds Provided
63 | Ssesse Island Boarding P/S | Primary | Kalangala | Construction of a boarding primary school (1st & 2nd Installment) | 1342979749 | 0 |  | 437035600 | 200000000 | 492633740 | 24631687 | 188678722 |  |  |  |  | 0 | Additional funds provided due to cost overruns
64 | St Peter P/S Semyungu | Primary | Luwero | Construction and refurbishment | 150000000 | 0 |  | 150000000 | 0 | 0 | [6 empty] | 0 | Completed
65 | St Stephen Nursery and Primary School Kyebando | Primary | Kampala | Construction of a primary school (1st & 2nd Installment) | 131000000 | 0 |  | 71000000 | 60000000 | 0 | [6 empty] | 0 | School closed
66 | St. Aloysius Core PTC Ngora 5 dec 2013 | PTC | Ngora | Renovation of old buildings | 601419258 | [11 empty] | 601419258 | Source of funding devt of PTCs
67 | St. Augustine PTC | PTC | Kyenjojo | Construction of a multi purpose hall and kitchen | 314751000 | [7 empty] | 200000000 | 114751000 |  |  | 0
68 | Summit View P/S Kololo | Primary | Kampala | Renovation of the primary school | 149999733 | 0 |  | 123753000 | 26246733 | 0 | [6 empty] | 0 | Funds Provided
69 | Rwesande SDA on 18th August, 2014 | Primary | Kasese | Construction of 8 classrooms, VIP latrines, Administrative Block and Library | 442005454 | [7 empty] | 211295053 | 230710401 |  |  | 0 | 3 Classroom Block at plastering and toilet is roofed and plastered
70 | Bukatira Primary school on 27th August, 2014 | Primary | Nakaseke | Construction of a 7 classroom block, a boys' and girls'VIP latrines, and an Administrative Block | 297806103 | [7 empty] | 150000000 | 147806103 |  |  | 0 | Completed construction of 4-Unit staff House, 4-Stance Vip and 4-Unit \\Kitchen
71 | Support to Science Students from Lango and Acholi sub regions. 23 sept 2010 | MoES |  | Average Tuition Cost for Science courses is UGX 2,284,000 per student per year; and UGX 1,610,000 per student per year for Arts Courses. | 0 | [11 empty] | 0 | Implemented under state house
72 | Bughanga Primary School 21 january 2014 | Primary | Butaleja | Construction of a modern Government aided primary school in Budumba sub-county, West Bunyole. | 491982560 | [11 empty] | 491982560
73 | Highland Community Primary School 21 jan 2014 | Primary | Butaleja | Construction of a four classroom block at Highland Community Primary School in Naweyo sub-county, Bunyole East. | 119593158 | [7 empty] | 119593158 |  |  |  | 0 | Completed and in use.
74 | Girls Boarding School 17th December 2014 | Primary | Namayingo | Build a Girls Boarding School in Sigulu Islands | 491982560 | [11 empty] | 491982560
75 | Kaguta Museveni Primary School 17th December 2014 | Primary | Mbale | Build a four classroom block | 167999204 | [11 empty] | 167999204
76 | Bulamba Primary School 17th December 2014 | Primary | Luwero | New building and renovation of Bulamba Primary School | 200000000 | [9 empty] | 200000000 |  | 0 | Guidelines and tender documents for construction of 2 classroom block with office and store furnished, 2 classroom block furnished, and 5 stance VIP latrine prepared and dispatched.
77 | Kalasa P/S 17 December 2014 | Primary | Luwero | New building and renovation of Kalasa Primary School | 999257158 | [11 empty] | 999257158 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
78 | Repair/renovation of 14 schools affected by floods 22nd December 2014 | Primary | Ntoroko | Repair/renovation of 14 schools affected by floods. The schools are Bwemarole P/S, Haibale P/S, Bugado P/S, Kabimbiri P/S, Kiranga P/S, Kasungu P/S, Budiba P/S, Masaka P/S, Kyabukuguru P/S, Great Valley P/S, Umoga P/S, Rwangara P/S, Kamuga P/S and New Hope P/S. | 500000000 | [8 empty] | 500000000 |  |  | 0 | Completed and commissioned a teachers house and 2stance VIP at kanyamukara plsch; construction of 2No. 2-classroom blocks at Ntoroko Primary School; construction of a 3-Classroom block at Rwamabale P/S; Construction of a 2-Classroom block at Umoja PS
79 | Kabatunda Primary School 9th February 2015 | Primary | Kasese | re-building of the school | 999257158 | [11 empty] | 999257158 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
80 | St. Kizito Boarding Primary School 25th February 2015 | Primary | Kyankwanzi | Reconstruction of the school. | 200000000 | [9 empty] | 200000000 |  | 0 | Prourement by district ongoing.
81 | Sam Iga Memorial Primary School 12th February 2015 | Primary | Luwero | Construction of a classroom block | 384665654 | [11 empty] | 384665654 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
82 | Mbarara Municipal School 10th March 2016 | Primary | Mbarara MC | Construction of a Modern Technical Workshop: i) establishment of 2 workshops (540,568,800/=), procurement of standard equipment) Areas are a workshop and classes for Food Science and Technology (100,000,000/=), Knitting and embroidery (150,000,000/=), Computer skills and technology (140,000,000/=), Carpentry and Joinery and Business management ( 150,000,000/=) | 1080568800 | [9 empty] | 500000000 | 400000000 | 180568800 | Construction of 3 storied workshop block ongoing and at roofing stage.
83 | Kal Aloi Parents School 3rd November 2015 | Primary | Agago | Build into a modern primary school with teachers' quarters. | 999257158 | [11 empty] | 999257158 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
84 | Yabwengi Primary School 27th January 2016 | Primary | Kiryandongo | Renovation of the school (including sanitation facilities) | 999257158 | [11 empty] | 999257158 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
85 | Bulanga Primary School 9th November 2016 | Primary | Luuka | rehabilitation of school structures | 999257158 | [10 empty] | 200000000 | 799257158 | To be implemented in FY 2018/19
86 | Kalongo Girls Primary School 9th November 2016 | Primary | Kalongo | Construction of one block of teachers' houses | 192376704 | [11 empty] | 192376704 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
87 | Kihanga Primary School | Primary |  | Provide support | 200000000 | [9 empty] | 200000000 |  | 0 | School received funds. Guidelines/tender documents for construction of 2No. 2 classrom blocks prepared.
88 | Buruunga Primary School 20th February 2017 | Primary | Kiruhura | Reconstruction of the school at Buruunga - Kazo County. | 999257158 | [10 empty] | 370486971 | 628770187 | To be implemented in FY 2018/19
89 | Kyakanyenya Primary School 23rd March 2017 | Primary | Lwengo | Grant aiding the school | [12 empty] | 0 | Forwarded to Primary department for consideration.
90 | Ringe Memorial School 27th October 2017 | Primary | Nebbi | Renovating 2 classrooms blocks, constructing more classrooms and provision of a safe water source. Upgrade to a secondary school. Located in Atego Subcounty. | [12 empty] | 0
91 | Mary Queen of Peace Mixed Day and Boarding Primary School 27th October 2017 | Primary | Gulu | Construction of a dormitory. | [12 empty] | 0
92 | St. Florence Nursery and Primary School 8th October 2017 | Primary | Jinja MC | Construction of a Nursery and Primary School at Kikaramoja Village, Masese III, Walukuba Division. | [12 empty] | 0
93 | Barlegi Primary School 11th December 2017 | Primary | Otuke | Completion of the school in Okwang subcounty (completion of 8 classroom block incl. library; construction of HT office, school store, teacher houses and latrines) | [12 empty] | 0
94 | Bombo UMEA Primary School 14th February 2018 | Primary | Luwero | Rehabilitation of the school | [12 empty] | 0
95 | Igrah Women Group (Primary school) | Primary | Arua | Construction of four classrooms | [12 empty] | 0
96 | Makerere Yellow Primary School - Kubiri 29th May 2018 | Primary | Kampala | Renovation and Rehabilitation of the school. | [12 empty] | 0
97 | Buterimire Primary School 25th May 2018 | Primary | Kamuli | Construction of Teachers' Houses and Fencing the school. | [12 empty] | 0
|  |  |  | Sub Total | 44968320986 | 316800000 | 2877500000 | 1974188840 | 1145883413 | 690633740 | 935879429 | 687689133 | 1725106715 | 1938247404 | 1540000000 | 1415486093 | 29920906219
1 | Aboke Girls 28 august 2008 | Secondary | Apac | Laboratory with furniture | 140000000 | 0 | 140000000 | 0 | 0 | 0 | [6 empty] | 0 | Work was completed. School topped up and constructed a storied building.
2 | Abongomola Seed Secondary School | Secondary | Apac | Construction of a Seed Secondary School | 412150464 | 0 |  | 0 | 133050000 | 201808000 |  | 77292464 |  |  |  |  | 0 | 2 classrooms and latrines completed, work in defects.
3 | Alito S.S.S. | Secondary | Apac | Purchase of a Lorry | 100000000 | 0 |  | 100000000 | 0 | 0 | [6 empty] | 0 | 100 million shillings disbursed to school in FY 2010/11
4 | Apac H.S | Secondary | Apac | Renovation | 120000000 | 0 | 120000000 | 0 | 0 | 0 | [6 empty] | 0 | School changed scope, without approval, 6 classrooms completed but floors are cracked, Administration finishes internally were poorly done, Laboratories not done.
5 | Biguli S.S | Secondary | Kamwenge | Construction of a Seed Secondary School (1st & 2nd Installment) | 374404356 | 0 |  | 70525000 | 162525000 | 102208500 |  | 39145856 |  |  |  |  | 0
6 | Kasenda S S 9 June 2013 | Secondary | Kabarole | Construction of a Seed Secondary School in Kasenda Subcounty which has no secondary School | 1503429000 | [11 empty] | 1503429000 | Site for construction identified as former St. Paul's High School, Nyabweya.
7 | Atyiak Memorial Girls Sec Sch 9 June 2013 | Secondary | Amuru | Construction of a Memorial Girls School in Atyiak sub county in memory of the LRA victims | 916707095.95 | [11 empty] | 916707095.95
8 | Lwala Girls SS 14 nov 2013 | Secondary | kaberamaido | Schoool bus for the School | 150000000 | [11 empty] | 150000000
9 | St. Aloysius College, Nyapea 8 feb 2014 | Secondary | Zombo | Fencing of the school | 10000000 | [11 empty] | 10000000 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
10 | Masese Secondary School 9 June 2013 | Secondary | Jinja MC | Construction of a secondary school on Jinja Municipality East Constituency | 916707095.95 | [7 empty] | 0 | 156498517.125 |  |  | 760208578.825 | Constructed and administration block with furniture; two 2 classroom blocks; two 5 stance waterborne toilets; and, 1 two stance waterborne toilet. Construction of a 2 unit science laboratory block stalled at roofing stage because of lack of funds.
11 | Support to Secondary schools in Buhweju 9 June 2013 | Secondary | Buhweju | Support to Secondary Schools by equipping Science and Computer laboratories | 240000000 | [7 empty] | 240000000 |  |  |  | 0 | There are four govt schs in Buhweju each provided science equipment of 20m/= and 20 computers at 2m/= each.
12 | Bishop ilukor Girls s.s.s | Secondary | Kumi | 2 classroom blocks and administration block. , 8 latrine stances and 2 laboratories. | 208000000 | 208000000 | [10 empty] | 0 | Completed
13 | Bubare S.S 29 sept 2009 | Secondary | Kabale | Construction of a science laboratory, library and state-of-the-art computer laboratory (1st & 2nd Installment) | 230000000 | 0 |  | 75000000 | 155000000 | 0 | [6 empty] | 0 | work at wall plate on the ICT laboratory.
14 | Buhweju SSS | Secondary | Bushenyi | 2 classroom blocks, laboratory, administrastion block, 8 stance latrine | 422926000 | 208000000 |  | 214926000 | 0 | [7 empty] | 0 | Completed
15 | Buremba S.S.S 1 june 2009 | Secondary | Kiruhura | Multi purpose Science room, Equipment and Dormitory; Purchase of School Lorry | 478250000 | 0 | 278250000 | 100000000 | 100000000 | 0 | [6 empty] | 0 | Completed
16 | Busedde S.S.S | Secondary | Jinja | 2 classroom blocks of 2 classrooms, 2 latrine blocks of 4 stances each, 2 laboratories and an administration block | 208000000 | 208000000 | [10 empty] | 0 | Completed
17 | Katakwi High School 17 nov 2013 | Secondary | Katakwi | School bus for the school | 150000000 | [7 empty] | 150000000 |  |  |  | 0
18 | Toroma SSS 17 nov 2013 | Secondary | Katakwi | School bus for the school | 150000000 | [8 empty] | 150000000 |  |  | 0
19 | Butte Parish 27 november 2012 | Secondary | Mayuge | Construction of a secondary Government School | 463154128 | [6 empty] | 203044850 | 260109278 |  |  |  | 0 | Completed
20 | Buyiga B S.S. | Secondary | Mpigi | Construction of a Secondary School (1st & 2nd Installment) | 284000000 | 0 |  | 70000000 | 214000000 | 0 | [6 empty] | 0 | Completed
21 | Bulamu Seed SS received on 28August 2014 | Secondary | Mpigi | Constuction of a Girl's Hostel | 141600000 | [11 empty] | 141600000
22 | Chegere S.S 1 june 2009 | Secondary | Apac | Science room | 70000000 | 0 | 70000000 | 0 | 0 | 0 | [6 empty] | 0 | work was completed
22 | Dokolo Girls S.S | Secondary | Dokolo | Model S.S.S (1st & 2nd Installment) | 388908080 | 0 |  | 70525000 | 108818333 | 151529101 |  | 58035646 |  |  |  |  | 0 | Construction of a 3 classroom block with an office completed.
23 | Dokolo Girls S.S | Secondary | Dokolo | Model S.S.S (1st & 2nd Installment) Phase 2 | 200000000 | [10 empty] | 200000000 | 0
24 | Galamba S.S.S | Secondary | Wakiso | 2 classroom blocks, administration block, 8 stances of latrines and a laboratory block. | 208000000 | 208000000 | [10 empty] | 0 | Completed
24 | Gamatui Girls Secondary School | Secondary | Kapchorwa | Construction of Basic infrastructure ICT Block; 2 Domitory blocks; 2 No. blocksof 5-stance lined latrines; Multipurpose dining Hall; Library block and Sick bay. | 394017413 | 0 |  | 251000000 | 0 | 103411000 |  | 39606413 |  |  |  |  | 0 | Construction of ground floor and columns for second floor of storied dormitory block completed.
25 | Gamatui Girls Secondary School | Secondary | Kapchorwa | Construction of Basic infrastructure ICT Block; 2 Domitory blocks; 2 No. blocksof 5-stance lined latrines; Multipurpose dining Hall; Library block and Sick bay. (Phase 2) | 200000000 | [10 empty] | 200000000 | 0
26 | Iguli Girls SS | Secondary | Dokolo | 5 classrooms completed, 1 Dormitory block, 5 Stance VIP latrines. | 120118200 | 0 |  | 0 | 100000000 | 0 | [6 empty] | 20118200 | 5 classrooms completed, Dormitory block at finishing stage with latrines.
27 | Immaculate Heart Nyakibaale Girls | Secondary | Rukungiri | Construction of ICT Laboratory. (Final provision ai additional on to the original budget for the storied building) | 241000000 | 0 | 120000000 |  |  |  | 121000000 | [5 empty] | 0 | school constructed a 4 storey structure with a top up from Parents. The school received addittional 120m in FY 2013/14.
28 | Isingiro S.S. | Secondary | Isingiro | 8 classroom, a library and completion of laboratories | 350000000 | 0 | 308000000 |  |  |  | 42000000 | [5 empty] | 0 | Civil works were completed as per report from EA.
28 | Our Lady of Guadalupe SSS 11th March 2015 | Secondary | Gomba | Construction of a laboratory block | 20000000 | [7 empty] | 20000000 |  |  |  | 0 | Funds released were for purchase of science laboratory equipment
29 | Our Lady of Guadalupe SSS 11th March 2015 | Secondary | Gomba | Construction of a laboratory block (Phase 2) | 200000000 | [10 empty] | 200000000 | 0
30 | Itendero Secondary School | Secondary | Bushenyi | Provide the School with 200 bags of cement and 200 iron sheets. | 9000000 | 0 | 9000000 | [9 empty] | 0 | Completed
31 | Kabarega S.S.S | Secondary | Masindi | Rehabilitation of the school (1st & 2nd Installment) | 200000000 | 0 |  | 70000000 | 88000000 | 0 |  |  |  | 42000000 |  |  | 0 | The storied structure under renovation was blown off by wind after re-roofing with new roof structure. Need for assessment.
31 | Kabbo Secondary School | Secondary | Mubende | Construction of a Secondary School (1st & 2nd Installment) | 729600000 | 445600000 |  | 70000000 | 214000000 | 0 | [6 empty] | 0 | Constructed 6 classrooms, two 5 stance VIP latrines and one 2 stance VIP latrine.
32 | Kabbo Secondary School | Secondary | Mubende | Construction of a Secondary School (1st & 2nd Installment) (Phase 2) | 200000000 | [10 empty] | 200000000 | 0 | More funds to be provided in FY 2018/19
33 | Mugungulu S S | Secondary | Mubende | Construction of a Secondary School IN Bagezza Sub county | 916707095.95 | [11 empty] | 916707095.95 | Completed
34 | Kigando S S | Secondary | Mubende | Construction of a Secondary School in Kigando Sub county | 916707095.95 | [11 empty] | 916707095.95
35 | Kamusenene S S | Secondary | Mubende | Construction of a Secondary School in Kitumbi sub county | 916707095.95 | [7 empty] | 306655610.875 | 200000000 |  |  | 410051485.075 | Constructed two 2 classroom blocks.
36 | Manyogaseka S S | Secondary | Mubende | Construction of a Secondary School in Manyogaseka sub county | 916707095.95 | [11 empty] | 916707095.95
37 | Makokoto S S | Secondary | Mubende | Construction of a Secondary School in makokoto sub county | 916707095.95 | [11 empty] | 916707095.95
38 | Kamuhingi Secondary School | Secondary | Bundibugyo | Construction of Hostel (1st & 2nd Installment) | 196000000 | 0 |  | 70000000 | 126000000 | 0 | [6 empty] | 0 | Scope was reduced to 2 dormitories due to low unit cost. One block completed.
39 | St. Kizito Secondary School 29-Aug-2015 | Secondary | Mityana | Construction Laboratory | 140000000 | [11 empty] | 140000000 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
40 | Bwizi Seed SS 21 june 2011 | Secondary | Kamwenge | Construction of seed Secondary School | 916707095.95 | 0 | [10 empty] | 916707095.95 | Completed
41 | Kamwenge (Bihanga) 21 june 2011 | Secondary | Kamwenge | Construction of seed Secondary School | 916707095.95 | 0 | [6 empty] | 200000000 |  |  |  | 716707095.95
42 | Kamwenge S.S | Secondary | Kamwenge | 2 unit school laboratory, library, 2 classrooms, 2 unit staff houses | 402000000 | 0 | 232000000 |  |  |  | 170000000 | [5 empty] | 0 | All structures incomplete
43 | Karangura SS 29 july 2012 | Secondary | Kabarole | Construction of a Secondary School in Karangura Sub county, Burahya County | 916707095.95 | [7 empty] | 200000000 | 163154128 |  |  | 553552967.95 | Constructed two 2 classroom blocks; two 5 stance VIP latrine; and, one 3 classroom block.
44 | Kasese Diocese Seminary Secondary School. 20 oct 2010 | Secondary | Kasese | Construction of Laboratory, laboratory equipment and furniture | 202000000 | [5 empty] | 202000000 | [5 empty] | 0
45 | Katakwi High School 3 dec 2011 | Secondary | Katakwi | Construction of a Girl's Hostel (capacity of 70 students) | 110219457 | 0 |  | 0 |  | 0 | 110219457 | [5 empty] | 0
46 | Katebwa SDA | Secondary | Kabarole | Iron sheets and cement | 10000000 | 0 | 10000000 | [9 empty] | 0 | Completed
47 | Kattalekamesse Modern S.S.S | Secondary | Nakaseke | Construction materials | 50000000 | 0 | 50000000 | 0 | 0 | 0 | [6 empty] | 0 | Funds Provided
48 | Kayoro S.S | Secondary | Busia | Renovation | 120000000 | 0 |  | 120000000 | 0 | 0 | [6 empty] | 0 | Completed
49 | Kibiito S.S 1 june 2009 | Secondary | Kabarole | 4 classroom block | 100000000 | 0 | 100000000 | [9 empty] | 0 | Funds Provided
50 | Ariwa, Kei, Midigo, Lodonga, Drajini, Romogi, Kerwa and Kululu 15 march 2014 | Secondary | Yumbe | Construction of 5 government aided secondary schools in sub counties without | 4583535479.75 | [11 empty] | 4583535479.75 | Awaiting site identification
51 | Kifamba Comprehensive S.S 28 sept 2009 | Secondary | Rakai | Rehabilitation of the school (1st & 2nd Installment) | 244000000 | 0 |  | 70000000 | 130000000 | 0 |  |  | 44000000 |  |  |  | 0
52 | Kikagate S.S 10 dec 2009 | Secondary | Isingiro | Construction of a Modern Secondary School (1st & 2nd Installment) | 284000000 | 0 |  | 70000000 | 214000000 | 0 | [6 empty] | 0 | Funds Provided
53 | Kinoni Community High School | Secondary | Kiruhura | Construction of a high school.Outstanding Bills/Debts on FY 2009/10 Presidential Pledges | 421400500 | 0 | 284450000 | 0 | 94769000 | 30500000 |  | 11681500 |  |  |  |  | 0
54 | Kinyogoga SSS | Secondary | Nakaseke | Turn school into boarding school under Universal Secondary Education (1st & 2nd Installment) | 637985951 | 0 |  | 119525000 | 169525000 | 252303652 |  | 96632299 |  |  |  |  | 0 | Work on dormitories was at final finishes.
55 | Kitagata S.S | Secondary | Bushenyi | Construction of science laboratories (Inclusive of furniture & equipment) | 144999999.625 | 0 |  | 40420630.625 | 34579369 |  | 70000000 | [5 empty] | 0
56 | Kitagwenda Comprehensive 1 june 2009 | Secondary | Kamwenge | 2-Unit Sc Lab, Lib, 2 Classrooms, 2-Unit Staff house (1st & 2nd Installment) | 374404356 | 0 |  | 70525000 | 162525000 | 102208500 |  | 39145856 |  |  |  |  | 0
56 | Kwosir Girls Secondary School | Secondary | Kween | Construction of a boarding secondary school for Sebei sub region | 1216623424 | 0 |  | 539050000 | 289050000 | 280928000 |  | 107595424 |  |  |  |  | 0 | Completed 2 classroom block and 3 classroom block with furniture; Completed dormitory block with beds. Administration block at plaster works.
57 | Kwosir Girls Secondary School | Secondary | Kween | Construction of a boarding secondary school for Sebei sub region (Phase 2) | 200000000 | [10 empty] | 200000000 | 0
58 | Kyezibire SSS | Secondary | Isingiro | Rehabilitation of the school | 100000000 | [11 empty] | 100000000 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
59 | Kyeizimbire S.S.S 11 feb 2008 | Secondary | Isingiro | Construction of 2 classroom block of 2 classrooms, administration block, a laboratory, 1 unit teacher's house, 2 latrine blocks of 5 stances and a dinning hall and kitchen. | 410000000 | 410000000 | [10 empty] | 0 | Completed
60 | Lake Mburo Resettlement Scheme 13 july 2009 | Secondary | Kiruhura | Provision of a school truck, Completion of Science laboratory with science equipment (1st & 2nd installment) | 427604238 | 0 |  | 130000000 | 160000000 | 44821000 | 75616795 | 17166443 |  |  |  |  | 0 | Completed
61 | Lake Mburo Resettlement Scheme 5 dec 2013 | Secondary | Kiruhura | Repair and rehabilitation of the school | 100000000 | [8 empty] | 100000000 |  |  | 0 | Completed library
62 | Makulubita Secondary School | Secondary | Luwero | Rehabilitation and construction of new structures | 634050000 | 0 |  |  | 0 | 350000000 |  | 134050000 |  |  |  | 150000000 | 0 | Constructed classrooms, toilet and administration block. Work on multipurpose hall stalled due to lack of funds.
63 | Makuutu Seed Secondary School | Secondary | Iganga | Additional funds to complete the construction works at Makuutu Seed school | 151526000 | [5 empty] | 151526000 | [5 empty] | 0 | Funds Sent
64 | Manze S.S | Secondary | Wakiso | Roofing a wo classroom block | 25000000 | 0 | 25000000 | [9 empty] | 0 | Completed
65 | Maruzi S.S | Secondary | Apac | Construction of a Seed Secondary School (1st & 2nd Phase) | 392614607 | 0 |  | 70525000 | 112525000 | 151529000 |  | 58035607 |  |  |  |  | 0 | 8 classrooms, Administration and Laboratory at ring beam level. Works were at finishing stage.
66 | Masulita S.S.S | Secondary | Wakiso | 2 classroom blocks, administration block, 8 stances of latrines and 2 units of laboratories. | 208000000 | 208000000 | [10 empty] | 0 | Completed
67 | Mbarara Army SS | Secondary | Mbarara | Required support yet to be identified | 330000000 |  |  | 61784497 | 94073885 | 0 | 174141618 | [5 empty] | 0 | Funds Provided
68 | Muhutwe Secondary School | Secondary | Tanzania | A domitory block with 60 students capacity (double beds), Laboratory equipment | 0 | [11 empty] | 0 | provided for under development of sec budget FY 2012/13
69 | Nakasongola Moslem Secondary School 5 march 2011 | Secondary | Nakasongola | Construction of school (1st & 2nd Installment) | 386891433 | 0 |  | 100000000 | 173000000 | 82351000 |  | 31540433 |  |  |  |  | 0 | Completed construction of a 2 classroom block with furniture, a multipurpose science block with furniture and a 5 stance lined VIP latrine. Works pending on external finishes, lightening protection, splash aprone, ramp, painting internal door shutters and furniture for the Administration block; construction of a 2 stance lined VIP latrine and 10,000 ltr rainwater harvesting tank.
70 | Ngarama S.S.S 11 feb 2008 | Secondary | Isingiro | 2 classroom blocks of 3 classrooms, 2 latrine blocks of 5 stances each, Administration, dinning Hall nd 2 staff houses | 397000000 | 397000000 | [10 empty] | 0 | Completed
71 | Ngarama S.S.S | Secondary | Isingiro | Rehabilitation of school | 100000000 | [8 empty] | 100000000 |  |  | 0 | all funds were disbursed. The mainhall has been renovated. Currently renovating two classroom blocks.
72 | Ngoma Secondary School | Secondary | Budaka | Construction of a Laboratory | 140000000 | 0 |  | 0 | 140000000 | [7 empty] | 0 | Completed
73 | Ngoma SSS | Secondary | Nakaseke | Turn school into boarding school under Universal Secondary Education (1st & 2nd Installment) | 647155034 | 0 |  | 115620000 | 148456000 | 276991348 |  | 106087686 |  |  |  |  | 0 | Work on dormitories was at roofing stage.
74 | Njangali Girls High School | Secondary | Hoima | Essential chemicals, Equipment, Apparatus and reagents for new Laboratory (Funds for 3 science kits & 2 chemical kits and lab equipment) | 20000000 | [7 empty] | 20000000 |  |  |  | 0
75 | Nkoowe High School (Private) | Secondary | Wakiso | Laboratory equipment | 20000000 |  |  | 20000000 | 0 | 0 | [6 empty] | 0 | Completed
76 | Nyamirama S.S | Secondary | Kanungu | Construction of Seed Secondary School | 353000000 | 0 | 353000000 | [9 empty] | 0 | Funds Provided
77 | Nyamiyaga Secondary School | Secondary | Tanzania | A domitory block with 60 students capacity (double beds), Laboratory equipment | 0 | [11 empty] | 0 | To be provided for under development of sec budget
78 | Obalanga Comprehensive Secondary School | Secondary | Amuria | Construction of a Secondary School (1st & 2nd Phase) | 324442267 | 0 |  | 70000000 | 114000000 | 101549000 |  | 38893267 |  |  |  |  | 0 | Completed
79 | Okapel High School | Secondary | Ngora | Construction of a Laboratory | 140000000 | 0 |  |  | 140000000 | [7 empty] | 0 | Completed
80 | Pokot Girls Boarding Secondary School | Secondary | Amudat | Construction of a boarding secondary school (1st & 2nd Phase) | 654297809 | 0 |  | 0 | 250430000 | 292023000 |  | 111844809 |  |  |  |  | 0 | Completed
81 | Pope Paul Anaka S.S | Secondary | Amuru | Renovation of the school | 120000000 | 0 | 120000000 | 0 | 0 | 0 | [6 empty] | 0 | Completed
82 | Rubongi Army SS | Secondary | Tororo | Support to the school | 200000000 | 0 |  | 100000000 | 100000000 | 0 | [6 empty] | 0 | school contructed 4 classroom so far and completed them.
83 | Rukoni S.S 1 june 2009 | Secondary | Ntungamo | Construction of a multi purpose science room | 68000000 | 0 | 68000000 | [9 empty] | 0 | Plumbing, and water supply, work tops were not done due to inssuficient funds.
84 | Rutooma S.S | Secondary | Mbarara | Rehabilitation of the school (1st & 2nd Installment) | 236280475 |  | 0 | 70000000 | 130000000 | 0 | 36280475 | [5 empty] | 0
85 | Rwot Acana Memorial College 3 july 2009 | Secondary | Gulu | Support to the school | 100000000 | 0 |  | 100000000 | 0 | 0 | [6 empty] | 0 | Funds received
86 | Buwambo Seed Secondary School | Secondary | Wakiso | Provision of 4 additional classrooms for expansion of the Seed Secondary School in Busukuma Sub-County | 203044850 | [6 empty] | 203044850 |  |  |  |  | 0
87 | Semuliki High School | Secondary | Bundibugyo | Construction of Hostel (1st & 2nd Installment) | 214000000 | 0 |  | 70000000 | 126000000 | 0 | 18000000 | [5 empty] | 0 | Completed
88 | Sselwanga Lwanga Memorial | Secondary | Kalangala | School bus | 100000000 | 0 | 100000000 | 0 | 0 | 0 | [6 empty] | 0 | Completed
89 | St Joseph Kinaba Community SS 25 july 2012 | Secondary | Kanungu | Elevation of school to a seed secondary school | 203044850 | 0 | [5 empty] | 203044850 |  |  |  |  | 0 | 4 classrooms completed.
90 | St Mary's College Kisubi | Secondary | Wakiso | Construction of a Memorial Dormitory | 1102019457 | 0 |  |  |  | 0 |  | 110219457 |  |  | 200000000 |  | 791800000 | Funds were used for renovation of old facilities.
91 | St. Michael's Girls Secondary School | Secondary | Kween | Construction of a Laboratory and Staff houses | 431794145 | 0 |  | 0 | 0 | 263050000 |  | 168744145 |  |  |  |  | 0
92 | St. Paul Biharwe H.S | Secondary | Mbarara | 200 iron sheets | 5000000 | 0 | 5000000 | [9 empty] | 0 | Completed
93 | Usuk Secondary School 17 nov 2013 | Secondary | Katakwi | Provision of a school bus | 150000000 | [6 empty] | 150000000 |  |  |  |  | 0
94 | St. Paul S.S Bukinda-Rukiga | Secondary | Kabale | Multi-Purpose Science room | 414500000 | 334500000 | 80000000 | [9 empty] | 0 | Awaiting Progress report on the works
95 | St.Mary's SSS Simbya (suribya SSS) | Secondary | Bundibugyo | Construction of Hostel (1st & 2nd Installment) | 196000000 | 0 |  | 70000000 | 126000000 | 0 | [6 empty] | 0 | Completed initial cost included beds
96 | Walibo Secondary School | Secondary | Luuka | Construction of Secondary School (1st & 2nd Installment) | 485129335 | 0 |  | 70500000 | 202000000 | 153745000 |  | 58884335 |  |  |  |  | 0 | 2 unit science laboratory was omitted due to high costs. 8 classrooms and administration completed and in use
97 | Ndagaro Seed Secondary School 5 november 2013 | Secondary | Rubirizi | Provision of a seed Secondary School in Ndangaro Sub-County | 916707095.95 | [11 empty] | 916707095.95
98 | Butologgo Seed Secondary School 10 January 2014 | Secondary | Mubende | Provision of a seed Secondary School in Butoloogo Sub-County | 916707095.95 | [11 empty] | 916707095.95 | Established under ADB III
99 | Budumba Community Secondary School 21 jan 2014 | Secondary | Butaleja | Construction of a four classroom block. | 119593158 | [7 empty] | 119593158 |  |  |  | 0 | Completed and in use.
100 | St. Joseph's S.S 27 nov 2013 | Secondary | Kyankwanzi | Rehabilitation of the school | 100000000 | [11 empty] | 100000000 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
101 | St. Mary's Madera Girls S.S.S | Secondary | Soroti | Construction of a dormitory. | 318000000 | [8 empty] | 148680000 |  |  | 169320000 | The school opted to complete the dormitory block started by the parents. Completed half of the block . The walls, roof, door and window frames and internal plaster are done.
102 | Nakyanyi Secondary School 17th December 2014 | Secondary | Lwengo | Renovate the school to be elevated to the standard of a government aided school. | 100000000 | [8 empty] | 100000000 |  |  | 0 | Completed.
103 | Jinja Secondary School | Secondary | Jinja | Rehabilitation of School Buildings. | 100000000 | [8 empty] | 100000000 |  |  | 0 | The school opted to construct a boundary wall.
104 | Nakabugu Seed School 17th December 2014 | Secondary | Luuka | Renovate the school to be elevated to the standard of a government aided school. | 100000000 | [8 empty] | 100000000 |  |  | 0 | Completed construction of a 2 classroom block.
105 | St. Henry's Kitovu | Secondary | Masaka | Build a science laboratory | 222360000 |  | 73680000 | [6 empty] | 148680000 |  |  | 0 | The BoG opted to construct a storied laboratory block. Works are still ongoing.
106 | Mbulamuti Secondary School 17th December 2014 | Secondary | Kamuli | Build a science laboratory for a Secondary School in Mbulamuti. | 148680000 | [8 empty] | 122327511 |  |  | 26352489 | The laboratory block constructed is at finishing stage and door and window frames are in place.
107 | Asinge Secondary School 22nd December 2014 | Secondary | Tororo | Acquisition of a school bus. | 150000000 | [10 empty] | 150000000 | 0 | To be implemented in FY 2018/19
108 | Mbarara Secondary School 29th November 2014 | Secondary | Mbarara | Acquisition of a school bus. | 150000000 | [11 empty] | 150000000 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
109 | Arengesiep Secondary School 17th October 2014 | Secondary | Nakapiripirit | Construct a girls' dormitory and a library; acquire a school lorry; construct teachers' houses | 538278904 | [11 empty] | 538278904 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
110 | Kijunjula Senior Secondary School | Secondary | luwero | Up-grading | 100000000 | [11 empty] | 100000000 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
111 | budago Senior Secondary School | Secondary | Nakaseke | Up-grading | 100000000 | [11 empty] | 100000000 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
112 | St. Joseph's Kinaaba Community Secondary School | Secondary | Kanungu | Provide support | 100000000 | [11 empty] | 100000000 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
113 | Stella Matutina Secondary School 7th February 2016 | Secondary | Kiryandongo | Construct a library, computer laboratory and purchase computers | 348673093 | [9 empty] | 348673093 |  | 0 | Stalled at Procurement.
114 | Kansanga Seed Secondary School 4th May 2016 | Secondary | Kampala | computers and 12 classrooms block and teachers' houses. | 664074264 | [11 empty] | 664074264 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
115 | kisozi senior secondary school 23rd may,2016 | Secondary | gomba | Fencing of the school | 10000000 | [11 empty] | 10000000 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
116 | kyogo senior secondary school 21st march,2016 | Secondary | kabale | rehabilitation of the school. | 100000000 | [11 empty] | 100000000 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
117 | St kizito secondary school-banda 29 august,2015 | Secondary | Mityana | construction fo a laboratory | 200000000 | [9 empty] | 200000000 |  | 0 | At procurement stage.
118 | St. Charles Lwanga SS Lwebitakuli 9th November 2016 | Secondary | Masaka | construction of classes, laboratory, library, teachers’ houses and latrine stances | 585783527 | [11 empty] | 585783527 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
119 | Abim Secondary School 9th November 2016 | Secondary | Kotido | construction of a VIP latrine | 24238557 | [11 empty] | 24238557 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
120 | St. Mary’s Rushoroza Vocational Secondary School 9th November 2016 | Secondary | Isingiro | build and grant aid school | 485129335 | [10 empty] | 250000000 | 235129335 | To be implemented in FY 2018/19
121 | Nyakayojo Secondary School 9th November 2016 | Secondary | Isingiro | construction of teachers' houses | 136290000 | [11 empty] | 136290000 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
122 | Ngora High School 17 November 2016 | Secondary | Ngora | Construction of a computer laboratory | 140000000 | [11 empty] | 140000000 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
123 | Kasenyi SS 5/12/16 | Secondary | Mubende | School bus for the School | 150000000 | [10 empty] | 150000000 | 0 | To be implemented in FY 2018/19
124 | Bumayoka Seed Secondary School | Secondary | Mbale | School bus for the School | 150000000 | [11 empty] | 150000000 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
125 | Secondary School 20th February 2017 | Secondary | Kiruhura | Construction of a modern secondary school at Buruunga - Kazo County. | 916707095.95 | [11 empty] | 916707095.95 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
126 | Noble Mayombo Memorial School 4th September 2014 | Secondary | Kabarole | Construction of a school | 916707095.95 | [11 empty] | 916707095.95 | Cost provided is an estimate. Funds shall be allocated for implementation of the pledge when availed by MoFPED
127 | Bishop Balya Community School 4th September 2014 | Secondary | Kabarole | Construction of a school | 916707095.95 | [9 empty] | 200000000 |  | 716707095.95
128 | Kirigwajjo SSS (Kambuga Kibaale High School) | Secondary | Kibaale |  | 200000000 | [9 empty] | 200000000 |  | 0 | At roofing stage.
129 | Kityerera SS | Secondary | Mayuge | Government take over of the school | [12 empty] | 0 | No additional wage provided
130 | Mukura Memorial Secondary School 3rd August 2015 | Secondary | Ngora | Purchase of a bus | [12 empty] | 0
131 | Kyamate Secondary School 26 April 2017 | Secondary | Ntungamo | Provision of school bus | 150000000 | [11 empty] | 150000000
132 | Ogor Seed Secondary School 23 dec 2013 | Secondary | Otuke | MoES takeover the school. | [12 empty] | 0 | No additional wage provided
133 | Kateebwa High School | Secondary | Kabarole | Grant Aid Kateebwa High School in Kateebwa Sub County. | [12 empty] | 0
134 | Katugunda Secondary School | Secondary | Kabarole | Grant Aid Katugunda Secondary School in Kabonero Sub County. | [12 empty] | 0
135 | Amugu Senior Secondary School 26th December 2014 | Secondary | Alebtong | Grant aid the school. | [12 empty] | 0
136 | Government Aided Secondary School 15th October 2014 | Secondary | Jinja | A Government Aided Secondary School for Buyengo Sub-county | [12 empty] | 0
137 | Namawanga Secondary School 9th November 2016 | Secondary | Mbale | requested to be grant aided | [12 empty] | 0 | School has been grant aided.
138 | Majanji SS 9th November 2016 | Secondary | Samia Bugwe | Grant aiding | [12 empty] | 0
139 | Ngora High School 17 November 2016 3rd March 2017 | Secondary | Ngora | Construction of a computer laboratory and provision of 20 computers. | [12 empty] | 0
140 | Buruunga Seed Secondary School 20th February 2017 | Secondary | Kiruhura | Construction of a modern secondary school at Buruunga - Kazo County. | [12 empty] | 0 | To carry out needs assesment
141 | Moroto High School 3rd August 2015 | Secondary | Moroto | Purchase of a bus | [12 empty] | 0
142 | Ikwera Girls' School 3rd August 2015 | Secondary | Apac | Purchase of a bus | 150000000 | [10 empty] | 150000000 | 0
143 | Alere Secondary School 3rd August 2015 | Secondary | Adjumani | Purchase of a bus | [12 empty] | 0
144 | Aculbanya Secondary School | Secondary | Kole | Purchase of a bus | [12 empty] | 0
145 | St. Peter's Secondary School, Mayungwe | Secondary | Butambala | Government take over of the school | [12 empty] | 0
146 | Mpungwe Secondary School 15th June 2017 | Secondary | Mayuge | Grant aid the school. | [12 empty] | 0 | Forwarded to Secondary department for consideration.
147 | Secondary School 17th July 2017 | Secondary | Arua | Construct a Seed Secondary School in Madi Okolo County | [12 empty] | 0
148 | Eluru Memorial Senior Secondary School 20th July 2017 | Secondary | Teso region | Complete construction of Secondary School in Kapelebyong | [12 empty] | 0
149 | Adilang Secondary School 9th August 2017 | Secondary | Agago | Develop school into a fully fledged boarding secondary school. Construct teachers' houses, school library, perimeter fence and dormitory facilities. Also provide a bus. | 1216623424 | [10 empty] | 200000000 | 1016623424
150 | Ngai Secondary School 30th August 2017 | Secondary | Oyam | Reconstruction of the school | [12 empty] | 0 | Yet to be costed.
151 | Busoga High School 25th September 2017 | Secondary | Kamuli | Infrastructure development | [12 empty] | 0 | Yet to be costed.
152 | Okum Seed Secondary School | Secondary | Otuke | Grant Aid the school. | [12 empty] | 0 | Forwarded to Secondary department for consideration.
153 | Model School 8th December 2017 | Secondary | Luuka | Construction of a model school in Bukapala village, Itakaibulu Parish | [12 empty] | 0
154 | St. Maria Gorret S.S.S Manyogaseka 5th February 2018 | Secondary | Mubende | Takeover the school in Kassanda South Constituency | [12 empty] | 0 | Forwarded to Secondary department for consideration.
155 | Bombo Senior Secondary School 14th February 2018 | Secondary | Luwero | Rehabilitation of the school and equipping science laboratory; Upgrade of metal works section to offer vocational training. | [12 empty] | 0
156 | Kako Senior Secondary School 14th March 2018 | Secondary | Masaka | Rehabilitation of the school (replacement of asbestos roofs) | [12 empty] | 0
157 | Francis Ayume Memorial Secondary School 5th March 2018 | Secondary | Koboko | Takeover the school. | [12 empty] | 0
158 | Rugarama Secondary School 22nd March 2018 | Secondary | Kamwenge | Grant aid the school. | [12 empty] | 0
159 | Nyakasenyi Secondary School 22nd March 2018 | Secondary | Kamwenge | Grant aid the school. | [12 empty] | 0
160 | Kanara Secondary School 22nd March 2018 | Secondary | Kamwenge | Grant aid the school. | [12 empty] | 0
161 | Kalasa College School COU, Wobulenzi 27th July 2018 | Secondary | Luwero | Construction of Staff houses | [12 empty] | 0
162 | Mwongyera Senior Secondary School 30th July 2014 | Secondary | Rubirizi | Grant aiding
163 | St. Basil SS (Our Lady of Apostles) 6th July 2018 | Secondary | Masaka | Construction of a computer room, a school library and an Administration Block
164 | Sacred Heart Senior Secondary School 14th June 2018 | Secondary | Gulu | Renovation of the school
165 | Ngogwe Baskerville Secondary School 9th August 2018 | Secondary | Lugazi MC | Construction of a science laboratory, library, computers, staff and transport facility
166 | St. Peters Warr Girls S.S.S 24th August 2018 | Secondary | Zombo | Provision of a school bus; construction of teachers' houses; constuction of school fence; recruitment of teachers.
167 | Christ The King SS Kalisizo 23rd August 2018 | Secondary | Kyotera | Provision of a school bus and ICT laboratory
|  |  |  | Sub Total | 49752452009.625 | 2627100000 | 2546380000 | 3239926127.625 | 4512326587 | 2940956101 | 1170784345 | 2063736190 | 1560358046.875 | 1631340156.125 | 1148673093 | 2050000000 | 24260871363
[6 empty] | FY 2008/09 | FY 2009/10 | FY 2010/11 | FY 2011/12 | FY 2012/13 | FY 2013/14 | FY 2014/15 | FY 2015/16 | FY 2016/17 | FY 2017/18 | FY 2018/19 | OUTSTANDING
|  |  |  | Primary | 44968320986 | 316800000 | 2877500000 | 1974188840 | 1145883413 | 690633740 | 935879429 | 687689133 | 1725106715 | 1938247404 | 1540000000 | 1415486093 | 29920906219
|  |  |  | Secondary | 49752452009.625 | 2627100000 | 2546380000 | 3239926127.625 | 4512326587 | 2940956101 | 1170784345 | 2063736190 | 1560358046.875 | 1631340156.125 | 1148673093 | 2050000000 | 24260871363
Note on E68: Jane: Source of funding Devt of PTCs
Note on R127: jnakajubi: Constructed storied dormitory
Note on R128: jnakajubi: Constructed storied dormitory
Note on J135: jnakajubi: innitial budget allocation 130m/=
Note on E138: jnakajubi: CHECK WHETHER NO SEED SCH HAS BEEN CONSTRUCTED THERE ADB
Note on O147: jnakajubi: inspected by sec dept.
Note on R150: jnakajubi: Costing borrowed from BTVET CMU costs
Note on R151: DNAMISI: Materials not yet delivered
Note on R156: jnakajubi: school indicates received 86m/= instead of 130m/= bal 44m/=
Note on I166: jnakajubi: transferred 80879470 instead of the budgeted 130m/=
Note on J166: jnakajubi: School received 133503735/= instead of the budgeted 160m/=
Note on K168: jnakajubi: 215m/= received instead of 350m/=
Note on D173: jnakajubi: total pledge was 330m/=
Note on I173: jnakajubi: Budget estimate was 100m/= the sch received 61,784,497/=
Note on J173: jnakajubi: budget estimate was 100m/= the sch received 94,073,885/=
Note on O174: Jane: Crosscheck with Sec whether it was provided for in FY 2012/13 Under sec devt
Note on R176: jnakajubi: Awaiting confirmation from sec dept. SEC indicateds affected by release cut yet progress 08/09 indicates complete structures.
Note on O183: Jane: Crosscheck with Sec whether it was provided for in FY 2012/13 Under sec devt
Note on F193: jnakajubi: original costing was 196m
Note on M196: jnakajubi: check cost
Note on O196: jnakajubi: check cost
Note on R198: DNAMISI: Materials not yet received
Note on R200: DNAMISI: Outstanding 18m
Note on B201: JANE NAKA: In the M&E data the name appears as in red.
Note on R201: jnakajubi: sec to confirm figures
Note on E204: jnakajubi: Ask if not under ADB
Note on H285: Recurrent budget from FY 2009/10 to stay in the budget for outer years
Note on I288: 0.3bn earlier contribution to Kumi Unv for a Bus has been added to Inter University Council on Approval of PS/ES after the TMM meeting held on 21st June 2010
Note on I289: Recurrent budget from FY 2009/10 to stay in the budget for outer years
Note on F301: jnakajubi: each computer estimated at 3m/=